## Action plan
AI Implementation Action Plan
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Stage / action | Owner | Deadline | Status | Notes
Stage 1 · Audit where you are — Survey existing AI use (formal and informal), staff confidence, policies, learner access. |  |  | Not started | Output: One-page snapshot
Stage 2 · Agree priorities and boundaries — Agree 2–3 priorities, boundaries, decision-makers and learner rules. |  |  | Not started | Output: Department AI position
Stage 3 · Evaluate tools — Check age, data, DPIA needs, accessibility, cost, impact, exit plan, staff testing. |  |  | Not started | Output: Approved tools register (formal approval only)
Stage 4 · Build staff capability — CPD, champions, inclusive practice, peer support. |  |  | Not started | Output: Termly CPD plan
Stage 5 · Prepare learners — Learner AI literacy, assessment expectations, safeguarding, access alternatives. |  |  | Not started | Output: Learner guide
Stage 6 · Review and adjust — Confidence, time, learner feedback, incidents, changing terms, improvements. |  |  | Not started | Output: Review record
Communicate department AI position to staff |  |  | Not started
Add AI misuse to malpractice policy (check JCQ guidance) |  |  | Not started
Schedule termly review |  |  | Not started
Statuses: Not started / In progress / Done / Blocked

## Risk log
AI Risk Log
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Risk | Likelihood (L/M/H) | Impact (L/M/H) | Owner | Mitigation | Review date
Personal data entered into unapproved AI tool | M | H |  | Training + approved tools only + safe-use checklist
AI-generated error reaches learners unchecked | M | M |  | Check-before-use rule; verification prompts
Assessment malpractice involving AI | M | H |  | Learner rules + acknowledgement + awarding-body guidance
Tool changes price/terms/age limits | M | M |  | Termly tool review + exit plan
Digital exclusion of learners without devices | M | M |  | Access alternatives + non-digital routes

## Decision log
AI Decision Log
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Date | Decision | Evidence / basis | Decided by | Review date
07/11/2026 | Example: department adopts approved tool X for drafting only | Tool review form completed; DPO consulted | Curriculum lead
Delete the example row before use.

## Audit calculator
AI Confidence & Digital Skills Audit — offline calculator
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Audit | Statement | Rating (1-4 or na)
AI Confidence Audit | I can explain in plain words what generative AI is.
AI Confidence Audit | I know AI can produce confident answers that are wrong.
AI Confidence Audit | I understand that AI tools can reflect bias.
AI Confidence Audit | I know the difference between a general chat tool and a tool my organisation has approved.
AI Confidence Audit | I can write a clear prompt that includes context, level and format.
AI Confidence Audit | I can improve an AI answer by asking a follow-up.
AI Confidence Audit | I can use AI to draft or adapt a lesson resource.
AI Confidence Audit | I can use AI to simplify or scaffold a text for different learners.
AI Confidence Audit | I can use AI to draft feedback that I then edit.
AI Confidence Audit | I check AI outputs for accuracy before using them.
AI Confidence Audit | I check outputs for tone, level and bias.
AI Confidence Audit | I make the final decision on anything that affects a learner’s progress.
AI Confidence Audit | I know what personal information must not be entered into AI tools.
AI Confidence Audit | I know who to ask about data protection and tool approval.
AI Confidence Audit | I know my organisation’s rules on AI use, or where to find them.
AI Confidence Audit | I understand copyright concerns when using AI or uploading other people’s work.
AI Confidence Audit | I know what to do if a learner meets something inappropriate or upsetting through AI.
AI Confidence Audit | I can explain to learners when AI use is and is not acceptable.
AI Confidence Audit | I can teach learners how to check AI answers.
AI Confidence Audit | I know where to find the awarding body rules on AI in assessment.
Digital Skills Self-Assessment | I can manage files and folders so I can find things quickly.
Digital Skills Self-Assessment | I can use email, calendars and online meeting tools.
Digital Skills Self-Assessment | I can search the web effectively and judge whether a source is trustworthy.
Digital Skills Self-Assessment | I can work with documents, spreadsheets and presentations.
Digital Skills Self-Assessment | I can share and collaborate on documents online.
Digital Skills Self-Assessment | I can use my organisation’s learning platform.
Digital Skills Self-Assessment | I can create simple digital resources, such as quizzes or short videos.
Digital Skills Self-Assessment | I can use polling, quizzes or other tools to check understanding.
Digital Skills Self-Assessment | I can adapt a lesson if the technology fails.
Digital Skills Self-Assessment | I can help learners who struggle with technology.
Digital Skills Self-Assessment | I can create accessible documents with real headings and clear structure.
Digital Skills Self-Assessment | I can add alt text to images and check colour contrast.
Digital Skills Self-Assessment | I can use text-to-speech or speech-to-text tools and show learners how.
Digital Skills Self-Assessment | I know several tools or strategies for different barriers to learning, and I do not assume one tool fits all.
Digital Skills Self-Assessment | I can spot phishing emails and suspicious links.
Digital Skills Self-Assessment | I use strong, separate passwords and know how to use two-step verification.
Digital Skills Self-Assessment | I know how to protect learners’ privacy and my own online.
Digital Skills Self-Assessment | I can teach learners about respectful online behaviour and what to do if they meet harm online.
Digital Skills Self-Assessment | I can help learners build digital skills that employers look for, such as communication, collaboration and basic data skills.
Digital Skills Self-Assessment | I feel able to try new technology without panic and I know where to find help.
Overall average (excludes na/blank):
Band: <1.75 Starting out · <2.55 Building · <3.35 Confident · 3.35+ Leading
Ratings: 1 Not yet · 2 With support · 3 Mostly confident · 4 Very confident · na = does not apply

## Team summary
Anonymous Team Summary — aggregated section averages only
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Section (AI audit) | Team average | Section (Digital audit) | Team average
Understanding AI |  | Everyday digital skills
Using AI in practice |  | Teaching with technology
Checking and judgement |  | Accessibility and inclusion
Safety, ethics and rules |  | Safety and online behaviour
Learners and assessment |  | Employability and emerging technology
Enter only aggregated, anonymous averages. Never enter individual responses. Individuals keep their own answers.

## CPD comparison
Free CPD Course Comparison
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Provider | Resource | Topic | Audience | Level | Duration | Cost | Account needed | Age rules | Credential | Accessibility statement | Official URL | Last checked
DfE | AI support materials | Generative AI in education (England) | School/college staff + leaders | Introductory | 4 staff modules + leaders' set | Free | No account stated | n.a. (staff CPD) | None — support materials | GOV.UK statement applies | https://www.gov.uk/government/collections/using-ai-in-education-settings-support-materials | 07/11/2026
UK government | AI Skills Boost (AI Skills Hub) | Practical AI skills for work | Every UK adult | Foundation | 20 min – 9 hrs per course | Free (Boost courses; wider catalogue ~60% paid — check each course) | Free learning profile | UK adults; no minimum age stated | Gov-backed virtual AI foundations badge (selected courses) | Check provider site | https://aiskillshub.org.uk/ | 07/11/2026
ETF | Enhance Digital Teaching Platform | FE digital teaching + EdTech/AI | FE teachers/trainers | Introductory | Micro-modules | Free | Free account (MyETF) | Not verified | Participation badges | Check provider site | https://enhance.etfoundation.co.uk/ | 07/11/2026
Jisc/AoC | Six FE AI principles (blog) | AI principles for FE | FE leaders/teachers | n.a. | Reading | Free | None | n.a. | None | n.a. | https://www.jisc.ac.uk/blog/six-ways-fe-colleges-can-help-learners-and-teachers-thrive-in-an-ai-enabled-world/ | 07/11/2026
IBM / City & Guilds Foundation | IBM SkillsBuild | AI, cyber, web dev, job readiness | UK jobseekers/adults | Introductory+ | Self-paced | Free | Register interest | Not stated | IBM digital badges | Check provider site | https://cityandguildsfoundation.org/skillsbuild | 07/11/2026
Open University | Digital skills: succeeding in a digital world | Digital confidence, online safety | Anyone | Level 1 introductory | ~24 hours (8 weeks × 3) | Free | Optional (start without) | Not stated | OU badge + Statement of Participation; CPD-accredited 24 points | Check provider site | https://www.open.edu/openlearn/course/view.php?id=6371 | 07/11/2026
Microsoft | Learn Educator Center — AI for education | AI resources for educators | Educators, leaders | Mixed | Self-paced | Free | Not verified | AI classroom toolkit 13–15 | None stated | Check provider site | https://learn.microsoft.com/en-gb/training/educator-center/topics/ai-for-education | 07/11/2026
Cisco | Networking Academy | AI, cyber, networking, programming | Self-paced learners | Introductory+ | 15–70 hrs per course | Free (most self-paced) | Account required | Generally 13+ (younger via managed school accounts) | Digital badges + completion certificates (not CCNA/CCST) | Check provider site | https://www.netacad.com | 07/11/2026
HP Foundation | HP LIFE | Business & digital skills incl. AI | Students, educators, lifelong learners | Introductory | Self-paced | Free | Join for free | Not stated | Certificate of Completion | Check provider site | https://www.life-global.org/ | 07/11/2026
AWS | Skill Builder | AWS cloud & AI training | Beginners to technical | Mixed | Self-paced | 1,000+ free items; some paid (Team subscription) | Sign-in referenced | Not stated | Badges; microcredentials (subscription) | Check provider site | https://skillbuilder.aws/ | 07/11/2026
Google | Applied Digital Skills | Practical digital skills video lessons | Educators and learners | Introductory | Lesson-based | Free | Not verified | Not stated | None stated | Check provider site | https://applieddigitalskills.withgoogle.com/en-GB/ | 07/11/2026
Raspberry Pi Foundation | Learn & Code Club | Coding and AI projects | Kids, teens, young adults | Introductory | Project-based | Free | Not verified | School-age (no specific limits stated) | None | Check provider site | https://www.raspberrypi.org/learn/ | 07/11/2026
Ocado Code for Life | Rapid Router | Gamified coding | Teachers and families | Introductory | Self-paced | Free | Not verified | Not stated | Printable club certificates | Check provider site | https://www.codeforlife.education/ | 07/11/2026
freeCodeCamp | Curriculum incl. AI engineering | Coding, AI, cybersecurity | Beginners to advanced | Introductory → advanced | Self-paced, project-based | Free | Account to save progress | Not stated | Free verified certifications (not regulated) | Check provider site | https://www.freecodecamp.org/ | 07/11/2026

## CPD tracker
CPD Tracker / Digital Skills Passport
Back in the Room Education · AI & Digital Learning Hub · 7 November 2026 · Back in the Room Education · backintheroomeducation.co.uk
Date | Course / resource | Provider | Why I chose it | Status | Credential earned | What I learned | Apply by
07/11/2026 | Example: DfE AI support materials — Module 1 | DfE | Starting point for AI guidance | In progress | None (support materials)
Delete the example row before use. Badges and certificates are not regulated qualifications.